## Team Metrics
Team Name - As Of: 10-Jun-20 | [19 empty] | Feature | Defects | Risks | Debts | Enablers
2020-06-10
|  | Team Stability | 88% | Sum of team growth (hours contributed by those outside the team) + shrinkage (hours given away by those in the team) over the past two weeks as a percentage of total team hours contributed | [7 empty] | Unplanned Work |  |  | 4w 7h | Amount of time remaining from the burndown at the end of the most recent sprint |  |  | Velocity | 5 | 3 | 6 | 2 | 5
[19 empty] | Baseline | 7 | 1 | 1.6667 | 1.3333 | 0.3
| Predictability | [9 empty] | Responsiveness
|  | Sprints Estimated | 1/20/97 |  | Sprint Velocity Done/Committed |  |  | 46.67% |  |  |  | Lead Time |  |  | 156 |  | Depoyment Frequency | 3
[19 empty] | Features | 0 | 3 | 9 | 2 | 6 | 4 | 5 | 2 | 13 | 9 | 0 | 5 | 90
[19 empty] | Defects | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 0 | 0 | 3 | 20
|  | Number of sprints worth of work on the backlog estimated in time/storypoints/t-shirt sizes. Good is 1/3/20 |  |  | Completed Story Points / Committed Story Points for the most recent sprint | [6 empty] | Median Lead Time (created - released) for Features released in the last 3 months |  |  |  |  | Number of code deployments in the previous calendar month (May) |  | Risks | 0 | 0 | 2 | 1 | 0 | 0 | 3 | 0 | 2 | 5 | 0 | 6 | 16
[19 empty] | Debts | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 2 | 12
[19 empty] | Enablers | 0 | 0 | 2 | 1 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 5 | 24
|  | TiP Variability | 60.9% |  | Sprint Output Variability |  |  | 51.9% |  |  |  | TiP |  |  | 73 |  | WiP | 7 |  | 2019-06-30 | 2019-07-31 | 2019-08-31 | 2019-09-30 | 2019-10-31 | 2019-11-30 | 2019-12-31 | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | Backlog
|  | Coefficient of Variability (Standard Deviation/ Average) for the PBIs TiP over the last 3 months |  |  | Coefficient of Variability for the team's velocity over the last 7 sprints | [6 empty] | Median Time in Process (start of 1st sprint - released) for PBIs released in the last 3 months |  |  |  |  | Maximum number of PBIs "In Progress" at the same time over the last 3 months
[23 empty] | T-5 | T-4 | T-3 | T-2 | T-1 | T |  | R | A | G | A | R
[19 empty] | Team Stability |  |  |  | 20% | 92.5% | 75% | 100% | 88% | 88% |  | <70% | <80% | 80-120% | >120% | >140%
| Produtivity | [14 empty] | Quality |  |  | Unplanned Work |  |  |  | 302400 | 504000 | 376200 | 347400 | 601200 | 601200 |  | >1w | >3d | <3d
[7 empty] | Release Velocity 10-Jun | Features |  | Efficiency |  |  | 1.362% |  |  |  | MTTR Mean Time to Resolve | 137.6
[8 empty] | Defects | [10 empty] | Sprints Estimated |  |  |  | 32.4699 | 39.7692 | 27.1667 | 14 | 17 | 20 |  | NA | NA | NA
[8 empty] | Risks | [10 empty] | Sprint Velocity |  |  |  | 5.172% | 26.32% | 64.15% | 100% | 83.78% | 46.67% |  | <60% | <80% | 80-120% | >120% | >150%
[7 empty] | Current versus 3 month avg. | Debts |  | Average of Active Time / Lead Team for the issues released in the last 3 months | [6 empty] | Average Lead Time for Bugs and Risks fixed in the last 3 months |  | TiP Variability |  |  |  | 76.03% | 76.03% | 79.12% | 84.01% | 132.2% | 60.9% |  | >50% | >25% | <25%
[8 empty] | Enablers | [10 empty] | Sprint Output Variability |  |  |  | 117.9% | 101.2% | 98.29% | 72.48% | 76.39% | 51.9% |  | >50% | >25% | <25%
[14 empty] | Distribution |  |  | Defect Density | 1% | Lead Time |  |  |  | 108.7692 | 108.7692 | 131.1111 | 133.5 | 110.4545 | 155.7727
[14 empty] | % allocation of PBIs (Features, Defects, Risks, Debts, Enablers) completed each month |  |  |  |  | Deployment Frequency |  |  |  | 1 | 1 | 1 | 1 | 0 | 3
[19 empty] | TiP |  |  |  | 70.1154 | 70.1154 | 70.0435 | 58.087 | 101.0714 | 72.9545
[17 empty] | Defects (in dev) and Bugs (in prod) raised during the last 3 months / man-days over the period |  | WiP |  |  |  | 5 | 5 | 3 | 7 | 7 | 7
[19 empty] | Efficiency |  |  |  | 1.14% | 1.407% | 1.649% | 1.697% | 1.362% | 1.362%
[17 empty] | Fail Rate | 0%
[19 empty] | Time to Resolve |  |  |  | 31.875 | 31.875 | 35.75 | 36 | 137.6 | 137.6
[19 empty] | Defect Density |  |  |  | 0.031469 | 0.02972 | 0.012324 | 0.017606 | 0.014388 | 0.01049
[17 empty] | Bugs (prod issues) with an Affects Version from the last 3 months of releases / Number of PBIs released over the same period |  | Fail Rate |  |  |  | 0.076923 | 0.2 | 0.11111 | 0 | 0 | 0
[19 empty] | Correct Status |  |  |  | 96% | 95.24% | 97.66% | 95.73% | 98.67% | 98.67% |  | <80% | <90% | >90%
[19 empty] | Correct Project & Epic Link |  |  |  | 92.97% | 94.62% | 95.52% | 96.92% | 99.39% | 99.39% |  | <80% | <90% | >90%
|  | Correct Status | 98.67% |  |  | Correct Project & Epic Link |  |  | 99.39% |  | Done In Sprint |  |  | 100% |  |  | Active Time % | 50% | Done In Sprint |  |  |  | 66.67% | 100% | 100% | 100% | 100% | 100% |  | <70% | <80% | >80%
[19 empty] | Active Time % |  |  |  | 1.25% | 26.74% | 12.5% | 36.46% | 50% | 50% |  | <50% | <80% | >80%
|  | Percentage of the Backlog that has the Status Category of "To Do" |  |  |  | Percentage of the Backlog and Active Sprint where the Epic and PBI are on the same project |  |  |  |  | For the most recent sprint the % of PBIs completed in the sprint verus those completed in and outside of the sprint | [5 empty] | Active Time logged in Jira per team member over the last two weeks as a % of total man hours
Scrum Team Stats - Template
Author: Ben Doughton, 2020