## Team Metrics
Team Name - As Of: 10-Jun-20 | [17 empty] | Feature | Defects | Risks | Debts
2020-06-10
|  | Team Stability | 88% | Sum of team growth (hours contributed by those outside the team) + shrinkage (hours given away by those in the team) over the past two weeks as a percentage of total team hours contributed | [5 empty] | Unplanned Work |  |  | 4w 7h | Amount of time remaining from the burndown at the end of the most recent sprint |  |  | Velocity | 5 | 3 | 6 | 2
[17 empty] | Baseline | 7 | 1 | 1.6667 | 1.3333
| Predictability | [7 empty] | Responsiveness
|  | Sprints Estimated | 1/20/97 |  | Sprint Velocity Done/Committed |  | 46.67% |  |  | Lead Time |  |  | 156 |  | Depoyment Frequency | 3
[17 empty] | Features | 0 | 3 | 9 | 2 | 6 | 4 | 5 | 2 | 13 | 9 | 0 | 5 | 90
[17 empty] | Defects | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 1 | 2 | 0 | 0 | 3 | 20
|  | Number of sprints worth of work on the backlog estimated in time/storypoints/t-shirt sizes. Good is 1/3/20 |  |  | Completed Story Points / Committed Story Points for the most recent sprint |  |  |  |  | Median Lead Time (created - released) for Features released in the last 3 months |  |  |  |  | Number of code deployments in the previous calendar month (May) |  | Risks | 0 | 0 | 2 | 1 | 0 | 0 | 3 | 0 | 2 | 5 | 0 | 6 | 16
[17 empty] | Debts | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 1 | 1 | 1 | 0 | 2 | 12
[18 empty] | 2019-06-30 | 2019-07-31 | 2019-08-31 | 2019-09-30 | 2019-10-31 | 2019-11-30 | 2019-12-31 | 2020-01-31 | 2020-02-29 | 2020-03-31 | 2020-04-30 | 2020-05-31 | Backlog
|  | TiP Variability | 60.9% |  | Sprint Output Variability |  | 51.9% |  |  | TiP |  |  | 73 |  | WiP | 7
|  | Coefficient of Variability (Standard Deviation/ Average) for the PBIs TiP over the last 3 months |  |  | Coefficient of Variability for the team's velocity over the last 7 sprints |  |  |  |  | Median Time in Process (start of 1st sprint - released) for PBIs released in the last 3 months |  |  |  |  | Maximum number of PBIs "In Progress" at the same time over the last 3 months
[21 empty] | T-5 | T-4 | T-3 | T-2 | T-1 | T |  | R | A | G | A | R
[17 empty] | Team Stability |  |  |  | 20% | 92.5% | 75% | 100% | 88% | 88% |  | <70% | <80% | 80-120% | >120% | >140%
| Produtivity | [12 empty] | Quality |  |  | Unplanned Work |  |  |  | 302400 | 504000 | 376200 | 347400 | 601200 | 601200 |  | >1w | >3d | <3d
[6 empty] | Release Velocity 10-Jun | Work Type | Efficiency |  |  | 1.362% |  |  |  | MTTR Mean Time to Resolve | 137.6
[7 empty] | Features | [9 empty] | Sprints Estimated |  |  |  | 32.4699 | 39.7692 | 27.1667 | 14 | 17 | 20 |  | NA | NA | NA
[7 empty] | Defects | [9 empty] | Sprint Velocity |  |  |  | 5.172% | 26.32% | 64.15% | 100% | 83.78% | 46.67% |  | <60% | <80% | 80-120% | >120% | >150%
[6 empty] | Current versus 3 month avg. | Risks | Average of Active Time / Lead Team for the issues released in the last 3 months | [6 empty] | Average Lead Time for Bugs and Risks fixed in the last 3 months |  | TiP Variability |  |  |  | 76.03% | 76.03% | 79.12% | 84.01% | 132.2% | 60.9% |  | >50% | >25% | <25%
[7 empty] | Debts | [9 empty] | Sprint Output Variability |  |  |  | 117.9% | 101.2% | 98.29% | 72.48% | 76.39% | 51.9% |  | >50% | >25% | <25%
[12 empty] | Distribution |  |  | Defect Density | 1% | Lead Time | 2019-09-30: 108.7692; 2019-10-31: 108.7692; 2019-11-30: 131.1111; 2019-12-31: 133.5; 2020-01-31: 110.4545; 2020-02-29: 155.7727
[12 empty] | % allocation of PBIs (Features, Defects, Risks, Debts, Enablers) completed each month |  |  |  |  | Deployment Frequency | 2019-09-30: 1; 2019-10-31: 1; 2019-11-30: 1; 2019-12-31: 1; 2020-01-31: 0; 2020-02-29: 3
[17 empty] | TiP | 2019-09-30: 70.1154; 2019-10-31: 70.1154; 2019-11-30: 70.0435; 2019-12-31: 58.087; 2020-01-31: 101.0714; 2020-02-29: 72.9545
[15 empty] | Defects (in dev) and Bugs (in prod) raised during the last 3 months / man-days over the period |  | WiP | 2019-09-30: 5; 2019-10-31: 5; 2019-11-30: 3; 2019-12-31: 7; 2020-01-31: 7; 2020-02-29: 7
[17 empty] | Efficiency | 2019-09-30: 1.14%; 2019-10-31: 1.407%; 2019-11-30: 1.649%; 2019-12-31: 1.697%; 2020-01-31: 1.362%; 2020-02-29: 1.362%
[15 empty] | Fail Rate | 0%
[17 empty] | Time to Resolve | 2019-09-30: 31.875; 2019-10-31: 31.875; 2019-11-30: 35.75; 2019-12-31: 36; 2020-01-31: 137.6; 2020-02-29: 137.6
[17 empty] | Defect Density | 2019-09-30: 0.031469; 2019-10-31: 0.02972; 2019-11-30: 0.012324; 2019-12-31: 0.017606; 2020-01-31: 0.014388; 2020-02-29: 0.01049
[15 empty] | Bugs (prod issues) with an Affects Version from the last 3 months of releases / Number of PBIs released over the same period |  | Fail Rate | 2019-09-30: 0.076923; 2019-10-31: 0.2; 2019-11-30: 0.11111; 2019-12-31: 0; 2020-01-31: 0; 2020-02-29: 0
[17 empty] | Active Time % |  |  |  | 1.25% | 26.74% | 12.5% | 36.46% | 50% | 50% |  | <50% | <80% | >80%
Scrum Team Stats - Template
Author: Ben Doughton, 2020